## Project Plan
[6 empty] | August | [5 empty] | September | [29 empty] | October | [30 empty] | November | [29 empty] | December
Requirement # | Requirement | Task # | Task | Estimate | Owner | 2019-08-26 | 27 | 2018-08-28 | 2018-08-29 | 2018-08-30 | 2018-08-31 | 2019-09-01 | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-14 | 2019-09-15 | 2019-09-16 | 2019-09-17 | 2019-09-18 | 2019-09-19 | 2019-09-20 | 2019-09-21 | 2019-09-22 | 2019-09-23 | 2019-09-24 | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-28 | 2019-09-29 | 2019-09-30 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-05 | 2019-10-06 | 2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-12 | 2019-10-13 | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-19 | 2019-10-20 | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-27 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2018-11-01 | 2018-11-02 | 2018-11-03 | 2018-11-04 | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-10 | 2018-11-11 | 2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16 | 2018-11-17 | 2018-11-18 | 2018-11-19 | 2018-11-20 | 2018-11-21 | 2018-11-22 | 2018-11-23 | 2018-11-24 | 2018-11-25 | 2018-11-26 | 2018-11-27 | 2018-11-28 | 2018-11-29 | 2018-11-30 | 2019-12-01 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06
2.1 | Research | 2.1.1 | Tech stack and methodology R&D | 8 days | Mitali/Gunjan/Lalitha/Kartik/Chen | bar: August 2018-08-28 to August 2018-08-29; September 2019-09-05 to September 2019-09-06; September 2019-09-11 to September 2019-09-12; September 2019-09-16 to September 2019-09-17; September 2019-09-23 to September 2019-09-24
2.2 | Project Setup | 2.2.1 | GCP Developer Account setup for chrome extension | 1 day | Mitali | bar: September 2019-09-25
|  | 2.2.2 | GCP Developer Account setup | 1 day | Karthik | bar: September 2019-09-26
|  | 2.2.3 | AWS Instance Setup | 1 day | Gunjan | bar: September 2019-09-26
|  | 2.2.4 | Database Setup | 1 day | Mitali | bar: September 2019-09-27
|  | 2.2.5 | Initial Starter Code - Backend | 2 days | Kartikeyan | bar: September 2019-09-27
|  | 2.2.6 | Initial Starter Code - Frontend | 2 days | Lalitha | bar: September 2019-09-30 to October 2019-10-01
2.3 | DataBase Design | 2.3.1 | Creating Schemas | 1 day | Gunjan | bar: September 2019-09-30
|  | 2.3.2 | Integrating Database to Backend | 2 days | Kartikeyan | bar: September 2019-09-30 to October 2019-10-01
2.4 | Web-Extension UI Design | 2.4.1 | Chrome Extension configuration setup | 2 days | Mitali | bar: October 2019-10-01 to October 2019-10-02
|  |  | Integrating compose box Gmail UI with chrome extension | 3 days | Mitali | bar: October 2019-10-03 to October 2019-10-04; October 2019-10-07
|  |  | Nudge UI changes | 2 days | Lalitha | bar: October 2019-10-04; October 2019-10-07
|  |  | Toggle UI changes | 2 days | Lalitha | bar: October 2019-10-02 to October 2019-10-03
|  |  | Compose box toolbox - Premium user UI | 2 days | Lalitha | bar: October 2019-10-08 to October 2019-10-09
|  |  | Compose box toolbox - Non Premium user UI | 2 days | Lalitha | bar: October 2019-10-14 to October 2019-10-15
2.5 | Register/ Login User | 2.5.1 | Sign-in UI page design | 3 days | Lalitha | bar: October 2019-10-21 to October 2019-10-23
|  |  | Integrating Sign in UI with front end & backend | 2 days | Mitali | bar: October 2019-10-24 to October 2019-10-25
|  | 2.5.2 | Backend: Create Social grant type login | 3 days | Kartikeyan | bar: October 2019-10-08 to October 2019-10-10
|  | 2.5.3 | Backend: Create User registration | 2 days | Kartikeyan | bar: October 2019-10-15 to October 2019-10-16
|  | 2.5.4 | Backend: Create User updation | 1 day | Kartikeyan | bar: October 2019-10-17
|  | 2.5.5 | Backend: Develop authorization paths and permissions | 1 day | Kartikeyan | bar: October 2019-10-21; October 2019-10-29 to October 2019-10-30
|  | 2.5.6 | Backend: Get Customer API | 2 days | Kartikeyan | bar: November 2018-11-04 to November 2018-11-05
2.6 | Storing Sent Email Meta-Data | 2.6.1 | Backend: save email meta data | 2 days | Kartikeyan | bar: November 2018-11-12 to November 2018-11-13
|  |  | Backend: update email meta data for any user | 2 days | Kartikeyan | bar: November 2018-11-14 to November 2018-11-15
|  |  | Backend: getCustomer API changes with view count | 2 days | Kartikeyan | bar: November 2018-11-21 to November 2018-11-22
2.7 | Read - Reciepts Tracking | 2.7.1 | Backend: Return tracking pixel for read reciepts | 2 days | Kartikeyan | bar: November 2018-11-27
|  | 2.7.2 | Backend: Create premium and non premium users | 1 day | Kartikeyan | bar: November 2018-11-28
2.8 | Adding Sonar Tag to Gmail | 2.8.1 | Embedding pixel image in mail body | 2 days | Mitali | bar: November 2018-11-28 to November 2018-11-29
2.9 | Integrating "Read-reciepts" to Gmail Sent Box | 2.9.1 | Integrating read receipts UI in Gmail Sent Box | 3 days | Gunjan
3.1 | Dashboard UI Development | 3.1.1 | User Dashboard UI design | 2 days | Chen | bar: October 2019-10-21 to October 2019-10-22
|  | 3.1.2 | Pricing details UI design | 2 days | Chen | bar: October 2019-10-28 to October 2019-10-29
|  | 3.1.3 | Queued emails UI design | 2 days | Chen
|  | 3.1.4 | Integrating User Dashboard with Gmail | 3 days | Lalitha | bar: November 2018-11-27 to November 2018-11-29
3.2 | Enable Toggle | 3.2.1 | Front end and back end integration for Toggle | 3 days | Gunjan | bar: October 2019-10-09 to October 2019-10-11
3.3 | Enable Nudge | 3.3.1 | Front end and back end integration for nudge | 2 days | Mitali | bar: October 2019-10-16 to October 2019-10-17
|  | 3.3.2 | API for nudge time set | 2 days | Kartikeyan | bar: October 2019-10-07; October 2019-10-11
|  | 3.3.3 | Create Nudge email with links | 2 days | Kartikeyan
|  | 3.3.4 | CronJob for Nudge check | 5 days | Kartikeyan | bar: November 2018-11-26 to November 2018-11-29
|  | 3.3.5 | Nudge delete | 1 day | Kartikeyan | bar: November 2018-11-25
3.4 | Create sonarAdmin service | 3.4.1 | Setup SonarAdmin backend started code | 1 day | Kartikeyan | bar: October 2019-10-01; October 2019-10-23
|  | 3.4.2 | Model changes for Admin | 1 day | Kartikeyan | bar: October 2019-10-22
|  | 3.4.3 | Password Oauth2.0 for Admin | 2 days | Kartikeyan | bar: October 2019-10-29; November 2018-11-01
|  | 3.4.4 | Admin registration with email service | 2 days | Kartikeyan | bar: November 2018-11-08; November 2018-11-12
|  | 3.4.5 | Admin double verification service | 2 days | Kartikeyan | bar: November 2018-11-13 to November 2018-11-14
|  | 3.4.6 | Admin Login API | 2 days | Kartikeyan | bar: November 2018-11-19
|  | 3.4.7 | Enaling admin authorisation for all APIS | 1 day | Kartikeyan | bar: November 2018-11-21 to November 2018-11-22; November 2018-11-28 to November 2018-11-29
|  | 3.4.8 | connect sonarAdmin to sonar and GetAllCustomer API | 2 days | Kartikeyan
|  | 3.4.9 | Change customer type API | 2 days | Kartikeyan | bar: November 2018-11-05
|  | 3.5.1 | Deploy Admin services to ec2 | 1 day | Kartikeyan
3.5 | Testing and bug fixes | 3.5.1 | Non-premium user end - to- end testing | 2 days | Chen | bar: November 2018-11-28 to November 2018-11-29
|  | 3.5.2 | Premium user end-to-end testing | 2 days | Mitali/ Gunjan/Lalitha | bar: November 2018-11-26 to November 2018-11-27
|  | 3.5.3 | Embedded pixel image broken bug fix | 2 days | Mitali
|  | 3.5.4 | Bug fix for myprofile dashboard | 1 day | Mitali | bar: November 2018-11-29
|  | 3.5.5 | Bug fix for sent box UI | 1 day | Gunjan | bar: November 2018-11-29
|  | 3.5.6 | User journey sign-in flow changes | 1 day | Mitali | bar: November 2018-11-28
3.6 | Documents | 3.6.1 | Requirement document | 1 day | Gunjan | bar: December 2019-12-02
|  | 3.6.2 | Technical design document | 1 day | Gunjan
|  | 3.6.3 | Test cases document | 2 days | Lalitha
|  | 3.6.4 | Client handover document | 1 day | Mitali/ Kartikeyan | bar: December 2019-12-05
Karthik
Chen
Lalitha
Mitali
Gunjan

## Test Plan
2.1 | Chrome Extension is visible on webstore
2.2 | Install Sonar from webstore
2.3 | Able to sign on using gmail in Sonar
2.4 | User can see the "This email is tracked by Sonar" while : Composing an email
2.5 | User can see the "This email is tracked by Sonar" while : Editing email from draft
2.6 | User can see the "read receipts" for past read emails from Sentbox
2.7 | Users can see "Read" when sent email is opened
2.8 | Users can see "Read" for multiple receipent in a dropdown
2.8.1 | For non-premium users: Users see the text "Read" for read emails
2.8.2 | For non-premium users: Users see the "Upgrade to Premium" option as a heyperlink while composing email
2.8.3 | For premium users: Users see the text "Read" and timestamp for read emails
2.9 | For premium users: Users see the options "Nudge" and "Toggle" while composing an email
3.1 | When user clicks on "Toggle" they should be prompted with a pop up "Turn off sonar for this email" which enables them to turn of read receipts for specific email
When user clicks on "Nudge" they should be prompted with a pop up "Alert me if reciepient" in which the user can select the receipient name from the drop down and will have option to enable alert within days, hours, minutes etc
1. User should receive an alert email saying the email has not been read within specified number of days (in case of enable alert within days) from the sent email date
2. User should receive an alert email saying the email has not been read within specified number of hours (in case of enable alert within hours) from the sent email time
3.2 | 3. User should receive an alert email saying the email has not been read within specified number of minutes (in case of enable alert within minutes) from the sent email time
3.3 | Receiver sees the text " This email is tracked by Sonar" in the emails received from a Sonar enabled sender
3.3.1 | Users should be able to view their registered account dashboard
3.3.2 | Dashboard shows user's Details - Name, email, Acccount Type
3.4 | Dashboard shows free and premium accounts details and costs
3.5 | Read receipt should be received once the receiver has opened the email which has Sonar tracking is enabled
3.6 | User metadata are being saved in AWS database